## Sheet1
Week | Term | Date | End Date | Important Dates | Milestones | Details | Current Progress
-1 | 2 | 2021-11-15 | 2021-11-21 |  | Buffer |  | x
0 | 2 | 2021-11-22 | 2021-11-28 |  | Write-Up the proposal |  | x
1 | 2 | 2021-11-29 | 2021-12-05 | Official Start of the Thesis | Finish up the draft proposal and conceptualize the methodology. |  | x
2 | 2 | 2021-12-06 | 2021-12-12 |  | Implement Next-Activity Prediction Model |  | x
3 | 2 | 2021-12-13 | 2021-12-19 |  | Implement Next-Activity Prediction Model |  | x
4 | 2 | 2021-12-20 | 2021-12-26 | Christmas Break | Buffer | Possible Literature Research | x
5 | 2 | 2021-12-27 | 2022-01-02 | Christmas Break | Buffer | Possible Literature Research | x
6 | 2 | 2022-01-03 | 2022-01-09 |  | Literature Research | Discrete Counterfactual Sequence Generation | -
7 | 2 | 2022-01-10 | 2022-01-16 |  | Literature Research | Evaluation Measures | -
8 | 2 | 2022-01-17 | 2022-01-23 |  | Choose Models for Counterfactual Generation and Evaluation Measures
9 | 2 | 2022-01-24 | 2022-01-30 |  | Write-Up: Introduction
10 | 2 | 2022-01-31 | 2022-02-06 |  | Write-Up: Literature Review
11 | 2 | 2022-02-07 | 2022-02-13 |  | Write-Up: Methodology
12 | 2 | 2022-02-14 | 2022-02-20 | End of Phase 1 | Send Draft 1 to Xixi
13 | 3 | 2022-02-21 | 2022-02-27 |  | Buffer
14 | 3 | 2022-02-28 | 2022-03-06 |  | Implement Experiment
15 | 3 | 2022-03-07 | 2022-03-13 |  | Implement Experiment
16 | 3 | 2022-03-14 | 2022-03-20 |  | Implement Experiment
17 | 3 | 2022-03-21 | 2022-03-27 |  | Implement Experiment
18 | 3 | 2022-03-28 | 2022-04-03 |  | Buffer
19 | 3 | 2022-04-04 | 2022-04-10 |  | Buffer
20 | 3 | 2022-04-11 | 2022-04-17 |  | Evaluate Results
21 | 3 | 2022-04-18 | 2022-04-24 |  | Evaluate Results
22 | 3 | 2022-04-25 | 2022-05-01 |  | Evaluate Results
23 | 3 | 2022-05-02 | 2022-05-08 |  | Buffer
24 | 4 | 2022-05-09 | 2022-05-15 |  | Write-Up: Experimental Results
25 | 4 | 2022-05-16 | 2022-05-22 |  | Write-Up: Evaluation
26 | 4 | 2022-05-23 | 2022-05-29 |  | Write-Up: Conclusion
27 | 4 | 2022-05-30 | 2022-06-05 |  | Buffer | ICPM: Possibly Paper Write-Up
28 | 4 | 2022-06-06 | 2022-06-12 | ICPM: Abstract Submissions | Buffer | ICPM: Possibly Paper Write-Up
29 | 4 | 2022-06-13 | 2022-06-19 | ICPM: Paper Submissions | Buffer
30 | 4 | 2022-06-20 | 2022-06-26 |  | Send Draft 2 to Xixi
31 | 4 | 2022-06-27 | 2022-07-03 |  | Finishing Touches
32 | 4 | 2022-07-04 | 2022-07-10 |  | Finishing Touches
33 | 4 | 2022-07-11 | 2022-07-17 | End of Phase 2 | Defense
34 | 4 | 2022-07-18 | 2022-07-24 | Summer Start | Defense
35 | 0 | 2022-07-25 | 2022-07-31 |  | Defense
36 | 0 | 2022-08-01 | 2022-08-07 |  | Defense
36 | 0 | 2022-08-08 | 2022-08-14 |  | Last Chance for Cum Laude
Formulas:
End Date = Table1[[#This Row],[Date]]+6